## Sheet1
|  |  |  | EXPECTED RESULT | ACTUAL RESULT
2026-09-09 | CH-1392 | Others | Chat --> send otp --> OTP is not being sent to the email. |  |  | High | Amirtha | Sasi | Open
2026-09-09 | CH-1380 | Others | Chat --> admin dashboard , customer representative dashboard ,supervisor dashboard , doctor --> profile --> Admin dropdown does not close when clicking outside the dropdown. | The Admin dropdown should close when the user clicks anywhere outside the dropdown | The Admin dropdown remains open even when clicking outside the dropdown. | Low | Amirtha | Sasi | Open
2026-09-09 | CH-1381 | Others | Chat --> admin dashboard --> profile --> Customer Representatives , Supervisors ,Chat Admins , Doctors --> table --> phone number --> its not US format | The phone numbers should be displayed in the standard US format: (XXX) XXX-XXXX | The phone numbers in the Customer Representatives, Supervisors, Chat Admins, and Doctors tables are not displayed in the US phone number format. | Low | Amirtha | Sasi | Open
2026-09-09 | CH-1382 | Others | Chat --> admin dashboard --> site settings --> system display something went wrong | The System section should load successfully without displaying any error message. | “Something went wrong” error message is displayed. | High | Amirtha | Sasi | Open
2026-09-09 | CH-1383 | Others | Chat --> all dashboard and patient dashboard --> open chat --> send document --> It should be displayed in blue color; currently, it looks like plain text. | The document sent through Open Chat should be displayed in blue color, indicating it as a clickable document/link. | When a document is sent through Open Chat, it is displayed as plain text instead of blue color. | Low | Amirtha | Sasi | Open
2026-09-09 | CH-1384 | Others | Chat --> all dashboard --> open chat --> Patient name should be displayed. | Patient Name should be displayed correctly. | Patient Name is not displayed | Low | Amirtha | Sasi | Open
2026-09-09 | CH-1385 | Others | Chat --> admin dashboard and customer representative dashboard --> complete chat --> first date is not working | first date filter should work correctly | he first date filter is not working as expected. | Low | Amirtha | Sasi | Open
2026-09-09 | CH-1386 | Others | Chat --> customer representative dashboard --> queued chat --> accept --> Blank page is displayed when opening a chat from the Active Chat Session | When opening a chat from the Active Chat Session, the chat details should be displayed correctly without showing a blank page. | Accept, a blank page is displayed when opening a chat from the Active Chat Session. | High | Amirtha | Sasi | Open
2026-09-09 | CH-1387 | Others | Chat --> customer representative dashboard --> ongoing chat --> chat --> Supervisor's name is displayed instead of the Representative's name and also Messages sent by the representative are displayed on the left side instead of the right side ( When a Representative sends a message, the Representative's name is not displayed correctly in the Supervisor Dashboard and Chat Admin Dashboard. Similarly, when a Supervisor or Chat Admin sends a message, their name is not displayed correctly in the Representative's chat.) | Representative's name should be displayed correctly, and Representative messages should be displayed on the right side. | Supervisor's name is displayed instead of the Representative's name, and Representative messages are displayed on the left side instead of the right side. | High | Amirtha | Sasi | Open
2026-09-09 | CH-1388 | Others | Chat --> supervisor dashboard --> New messages sent by the patient are not displayed in the open chat in real time. The messages appear only after navigating to another page and returning to the chat. | New messages sent by the patient should be displayed in the open chat in real time without navigating to another page. | New messages sent by the patient are not displayed in the open chat in real time and appear only after navigating to another page and returning to the chat. | High | Amirtha | Sasi | Open
2026-09-09 | CH-1389 | Others | chat --> all dashboard --> ongoing chat --> sender's profile picture is not displayed when sending a message | The sender's profile picture should be displayed along with the message. | The sender's profile picture is not displayed when sending a message. | Low | Amirtha | Sasi | Open
2026-09-09 | CH-1390 | Others | chat --> doctor dashboard --> queued chat , active chat session and ongoing chat --> Chat messages are not displayed | Chat messages should be displayed correctly in the Queued Chat, Active Chat Session, and Ongoing Chat sections. | Chat messages are not displayed in the Queued Chat, Active Chat Session, and Ongoing Chat sections. | High | Amirtha | Sasi | Open
2026-09-04 | CH-1335 | Others | Chat --> all dashboard --> delegate is not working | available staff members should be displayed in the dropdown list for chat delegation. | Staff members are not displayed in the dropdown list when attempting to delegate a chat. | High | Amirtha | Sasi | Open
2026-09-04 | CH-1336 | Others | Chat --> all dashboard --> private chat is not working | available staff members should be displayed in the dropdown list for private chat | Staff members are not displayed in the dropdown list when attempting to start a private chat. | High | Amirtha | Sasi | Open
2026-09-04 | CH-1336 | Others | Chat --> all dashboard --> group chat is not working | available staff members should be displayed in the dropdown list for group chat | Staff members are not displayed in the dropdown list when attempting to create a group chat. | High | Nayana | Sasi | Open
2026-08-28 | CH-1290 | Others | Chat --> chatadmin --> complete chat -->Doctor dropdown list overlaps with underlying doctor details | The Doctor dropdown list should be displayed properly without overlapping the underlying doctor details. | The Doctor dropdown list overlaps with the underlying doctor details. | Low | Amirtha | Suresh | Open

## Sheet3
chat
2026-09-10 | Count | Minor | Major | Total | Remaining Bugs
| Bugs | 7 | 9 | 16 | 16
| New Bugs Today | 6 | 6 | 12
Resolved Today in local
| Open Bugs | 7 | 9 | 16
Closed Bugs
Total bugs closed Today